## Sheet2
No | Directorat Key Result | Individual Goals GM NSA Jateng DIY | Individual Goals Level 3 | Individual Goals Level 2 dan Level 1 | Description Activity | additional Info | Siteid | sitename | Kabupaten | DO/Subdept | NS/ Departement | PIC | target Quartal | Date | Remark | Budget | Cost (Rp) | Status | Week Execute | Date Execute
1 |  | Availability & Operation | Alarm | Unproper Configuration | eGBTS Program | Already RRU | SMG106 | Bergas | SEMARANG | DEMAK | SEMARANG | RTPO, NS, TI | Q1 | Jan-Sep | Non POI RAFI | - | 0 | NY
2 |  | Availability & Operation | Alarm | Unproper Configuration | eGBTS Program | Already RRU | UNR707 | Beringin Relok | SEMARANG | DEMAK | SEMARANG | RTPO, NS, TI | Q1 | Jan-Sep | Non POI RAFI | - | 0 | NY
3 |  | Availability & Operation | Alarm | Unproper Configuration | eGBTS Program | Already RRU | SMG103 | Getasan | SEMARANG | DEMAK | SEMARANG | RTPO, NS, TI | Q1 | Jan-Sep | Non POI RAFI | - | 0 | NY
4 |  | Availability & Operation | Alarm | Unproper Configuration | eGBTS Program | Already RRU | UNR616 | Kopeng | SEMARANG | SEMARANG | SEMARANG | RTPO, NS | Q3 | Jan-Sep | Non POI RAFI | - | 0 | Done | 8 | 2023-02-23